## Sheet1
Iteration 1, 1 Month 7/1/17 - 7/31/17 | Iteration 2, 1 Month 8/1/17 - 8/31/17 | Iteration 3, 1 Month 9/1/17 - 9/30/17
UC04. Login | UC01. Search for Programs | UC02. Display Program Detail
Points: 3 | Points: 2 | Points: 2
Priorty: 1 | Priorty: 5 | Priorty: 5
Depends on: none | Depends on: none | Depends on: UC01
UC03. Submit Online Application | UC06. Edit Online Application | UC07. Check Application Status
Points: 5 | Points: 5 | Points: 5
Priorty: 1 | Priorty: 4 | Priorty: 5
Depends on: UC06 | Depends on: UC02, UC08, UC09 | Depends on: UC03
UC08. Submit Recommendation | UC09. Approve Course Equivalency Form | UC05. Logout
Points: 4 | Points: 5 | Points: 2
Priorty: 2 | Priorty: 2 | Priorty: 3
Depends on: UC05 | Depends on: UC05 | Depends on: UC04
Assumptions: (1) The team can produce 3 points of work per week. (2) Priorities are ranked from 1 to 5 with 1 being the highest.
Top Five Possible Risks | Risk | Risk Resolution Measures | Justification
UC03. Submit Online Application | High | Create a counter so that only allows a certain number of applications to be submited at a time and the rest placed in a queque to be accepted in the order they were entered | There can be an overload of submitted applications and the website can crash.
UC06. Edit Online Application | High | Create a page that shows the applications to be submited and highligh any changes made. | Edited information mnay not save, causing submitted information to not be accurate.
UC08. Submit Recommendation | High | Have system send confermation email with confermation number. | Multiple recommendations can be enter causing the website to crash or not be uploaded.
UC09. Approve Course Equivalency Form | High | Ensure that the form is consantly updated so that accurate information is displayed. | Information may not be displayed or displayed incorrectly.
UC05. Logout | High | Crete a time out action if the website is inactive after a certain amount of time. | User may log out but the system may remain logged in, causing security problems.
May Need Less Time | Reason | May Need More Time | Reason
UC05. Logout | Website closed out by user | UC03. Submit Online Application | Information must be entered and stored correctly
UC04. Login | Information entered by user to access website | UC06. Edit Online Application | Information must be entered and stored correctly
UC01. Search for Programs | Information displayed from already created system | UC08. Submit Recommendation | Information must be entered and stored correctly
UC02. Display Program Detail | information displayed from already created system | UC09. Approve Course Equivalency Form | information must be entered and stored correctly
UC07. Check Application Status | information displayed from already created application